## Slide 1: New Trust Plan outline and clinical considerations
We need to align with local policy and strategic aims ( identify gaps for development where MaST can support )
Embed at the start, identify the expectation to participate
Borrowed authority within the organization – identify sponsor
Identify progress -reporting upwards chain into steering group
Deliver an engagement plan to the trust with the intervention focus
Establish this with the steering group setting expectation to join and feedback
Book 1:1 coaching session with managers for intervention (f2f2 or teams )
Set up timetable for intervention (30 mins weekly for six session) keep this team focused to avoid drop out and disengagement )
Asking Ops Leads to present the intervention plan to steering group it supports internal ownership
follow up meetings - 4 weeks after final session – 8 weeks after final session

## Slide 2: Activity: Use of RTMO page in proactive discharge planning
Questions for team leads and supervisors
How is it used in supervision ?
Is RTMO used routinely as part of review
Working with the leads to embed review of RTMO
Scoping processes ( TS/caseload recduction)
Identify designated staff with responsibility for identification
Working with a manager or a designated lead on a regular basis to coach and support

## Slide 3: Discharge pathway planning Step-by-Step
Look at RTMO page
Sort alphabetically
Apply not seen for 20 weeks filter
OR
Apply sort by contact frequency and identify legacy cases
Delegate actions

## Slide 4: Activity: Use of MaST in Patient risk management
Questions for team leads and supervisors
How can it be used in zoning?
Is CFES used routinely as part of review
Working with the leads to embed review of CFES
Scoping processes
Identify designated staff with responsibility for identification
Working with a manager or a designated lead on a regular basis to coach and support

## Slide 5: Proactive support for safety huddles Step-by-Step
Look in CFES and/or CMHT
Apply Urgent 7 filter
Delegate Actions
Look in In Crisis page
Check that SU's have been followed up
Delegate actions

## Slide 6: Approaching this with teams
Challenges in knowledge and training :
Competing priorities in an MDT
Needs to be effort up front with managers and leads for specific task
Feeling under confident with using it in front of other staff
Not knowing how it works or how it helps
Competing time priorities for other stuff

## Slide 7: Outcomes focused
What do we want to measure:
Reduction in short term
Increase in discharged volume
total caseload volume reduction over time – metric reporting monthly
Number of discharges during the intervention
Number of SU not seen for 6 months
Pre clinic prep - Identify discharge process - opt in letter- review -support admin to feed into clinic -admin job to begin with – tidying up of caseload

## Slide 8: Activity: Use of MaST in supporting vulnerable cohorts
Asking them to :
Zoning meeting use - are they recording zoning in EPR/do we have it in MaST
Review Urgent 7 cohort - check for follow up
Review in patient / crhtt list – check for follow ups
What will we measure :
Increase of SU followed up within 7 days after urgent care presentation
Increase in SU with CMHT contact within 4 weeks during crisis
Increase in ‘red zone’ SU seen in 7 days
Completion of risks review within 7 days of crisis care

## Slide 9: Feedback
We use MAST in Team 1 MDTs in these ways:
· Those who haven’t been seen for 28days + (consider for enhanced support filter by 28+ toggle)
· Non allocated health care professional (in CMHT filter by no HCW)
· Breaches in 72 hour discharge (discharged from inpatient)
· Patients in contact with urgent care services in the last 7 days
We also use it to monitor CPA paperwork - care plan, risk assessment and others.
We use MAST in Team 2 MDTs in the below way
· Those who haven’t been seen for 28days + (consider for enhanced support filter by 28+ toggle)
· Non allocated health care professional (in CMHT filter by no HCW)
· Breaches in 72 hour discharge (discharged from inpatient)
· Patients in contact with urgent care services in the last 7 days
We also use it for monitoring of our inpatients and patients open to crisis services, I’ve attached a copy of the blank minutes for clarification,
In Team 3 we do use MaST in MDT in the following ways.
· Those who have not been seen for 28 days (step down for PCN/GP/Positive Pathway).
· Patients in contact with Urgent Care Services
· Oversight of unallocated cases
· Those cohort of patients that are emerging in crisis.
· Those requiring follow up after a period of inpatient care.